## Tasks
Section | Task | Subtask | Status | Priority | Owner | Due Date | Notes | Link | New
Task Management | Update 20251201 Tri Vananda Marketing Plan.xlsx |  | Not started | High | Yaya | 2026-07-14
Task Management | Create Master Strategic Campaign — Montara perspective |  | Not started | High | Tree |  | Science ¦ Art ¦ Soul framework across all brands and touchpoints
Events | Secure GWS Collaboration contract |  | Not started | High | Tree |  | Foundation for all GWS activity — prioritise
Events | BEING 2026 |  | Not started | High | Fon | 2026-09-02 | Wednesday 2 September 2026
Events | BEING 2026 | Booth showcasing Tri Vananda with the most updated information | Not started
Events | BEING 2026 | PRU Farm Festival advertising at the booth | Not started
Events | BEING 2026 | Booth production — design, build quotation, collateral print (lead time before 2 Sep) | Not started | [5 empty] | Yes
Events | PRU Farm Festival |  | Not started | High | Fon | 2026-11-01 | Sunday 1 November 2026 — collaborate to support them
Events | PRU Farm Festival | Vendor co-ordination support | Not started
Events | PRU Farm Festival | Activities support | Not started
Events | PRU Farm Festival | Manpower support | Not started
Events | GWS Tours — CLP / Farm |  | Not started | High | Yaya | 2026-11-09 | Monday 9 November 2026
Events | GWS Tours — CLP / Farm | Introducing session at CLP — Masterplan + TV showcasing Residential Villa | Not started
Events | GWS Tours — CLP / Farm | CLP estate tour | Not started
Events | GWS Tours — CLP / Farm | Buggy cruise through Tri Vananda landscape | Not started
Events | GWS Tours — CLP / Farm | Farm tour | Not started
Events | GWS Tours — CLP / Farm | Move to Trisara — PATAMA wellness tour and lunch | Not started
Events | Local Roots |  | Not started | High | Fon | 2026-11-14 | Saturday 14 November 2026
Events | GWS Tours — CLP / Local Roots |  | Not started | High | Yaya | 2026-11-14 | Saturday 14 November 2026
Events | GWS Tours — CLP / Local Roots | Introducing session at CLP — Masterplan + TV showcasing Residential Villa | Not started
Events | GWS Tours — CLP / Local Roots | CLP estate tour | Not started
Events | GWS Tours — CLP / Local Roots | Buggy cruise through Tri Vananda landscape | Not started
Events | GWS Tours — CLP / Local Roots | Local Roots | Not started
Events | GWS Tours — CLP / Local Roots | Move to Trisara — PATAMA wellness tour and lunch | Not started
Events | Exclusive Dinner at the Farm — GWS |  | Not started | High | Fon |  | Date TBC
Events | Exclusive Dinner at the Farm — GWS | Farm tour | Not started
Events | Exclusive Dinner at the Farm — GWS | Cocktail reception | Not started
Events | Exclusive Dinner at the Farm — GWS | Dinner | Not started
Events | Exclusive Dinner at the Farm — GWS | Entertainment | Not started
Events | Exclusive Dinner at the Farm — Potential Buyers, Partners & Media |  | Not started | High | Fon |  | Date TBC
Events | Exclusive Dinner at the Farm — Potential Buyers, Partners & Media | Property tour | Not started
Events | Exclusive Dinner at the Farm — Potential Buyers, Partners & Media | Cocktail reception | Not started
Events | Exclusive Dinner at the Farm — Potential Buyers, Partners & Media | Dinner | Not started
Events | Exclusive Dinner at the Farm — Potential Buyers, Partners & Media | Entertainment | Not started
New Online Ad Campaign | New campaign — Wellness theme |  | Not started | High | Tree |  | Science ¦ Art ¦ Soul
New Online Ad Campaign | Audience targeting |  | Not started | High | Tree |  | Luxury-wellness expats in Thailand, Southeast Asia and Australia
New Online Ad Campaign | Campaign infrastructure |  | Not started | High | Tree |  | Landing page, lead capture, KPI targets, budget approval — before launch |  | Yes
Marketing Collateral | PATAMA Residences CGIs |  | Not started | High | Yaya
Marketing Collateral | Tower Sign |  | Not started | High | Yaya
Marketing Collateral | Tower Sign | Signage design with logos | Not started
Marketing Collateral | Tower Sign | Tri Vananda and CLP to confirm logo | Not started
Marketing Collateral | Tower Sign | Update quotation and timeline | Not started
Marketing Collateral | Tower Sign | Select contractor | Not started
Marketing Collateral | Tower Sign | Get approval from CEO | Not started
Marketing Collateral | New Asset Library |  | Not started | High | Yaya
Marketing Collateral | Nanda A6 photos |  | Not started | High | Tung
Marketing Collateral | Nanda G88 photos |  | Not started | High | Tung
Marketing Collateral | Marketing Item Directory |  | Not started | High | Yaya
Marketing Collateral | Event Co-ordination SOP |  | Not started | High | Fon
Marketing Collateral | Giveaways order — Tote bags |  | Not started | High | Fon |  | Two versions: one premium, one giveaway
Marketing Collateral | Giveaways order — Tote bags | Get quotations and create email with details | Not started
Marketing Collateral | Giveaways order — Tote bags | Send to Khun Kitt for approval | Not started
Content Marketing | Q3–Q4 2026 social media plans |  | Not started | High | Yaya |  | Monthly plans through year-end, aligned to Sep–Dec launch arc
Content Marketing | Q3 2026 Quarterly Newsletter |  | Not started | High | Yaya
PR | Secure contract with J/PR |  | Not started | High | Tree
PR | Q3–Q4 2026 PR strategy and plan |  | Not started | High | Tree
PR | Strategic launch Sep–Oct, full amplification Nov–Dec |  | Not started | High | Tree
PR | Press kit / media fact sheet refresh |  | Not started | High | Tree |  | Ready for J/PR the day the contract signs |  | Yes
PATAMA | Source creative agency |  | Not started | High | Tree
PATAMA | YPO Retreat Package |  | Not started | High | Tree
PATAMA | GWS Retreat Package |  | Not started | High | Tree
PATAMA | Marketing collateral |  | Not started | High | Tree
PATAMA | Marketing collateral | Website | Not started
PATAMA | Marketing collateral | PATAMA Brochure — CLP Retreat | Not started
PATAMA | Marketing collateral | PATAMA Brochure — Trisara Retreat | Not started
PATAMA | Marketing collateral | PATAMA Wellness at Trisara menu | Not started
PATAMA | Social media |  | Not started | High | Tree
PATAMA | Digital ad campaign |  | Not started | High | Tree
PATAMA | Products for sale and giveaway |  | Not started | High | Tree |  | From local suppliers — e.g. wan sao long

## Key Dates
Label | Date
Marketing Plan xlsx due | 2026-07-14
BEING 2026 | 2026-09-02
PRU Farm Festival | 2026-11-01
GWS Tour — Farm | 2026-11-09
GWS Tour — Local Roots | 2026-11-14

## ReadMe
TRI VANANDA — TASK LIST DATA FILE
This file feeds the dashboard: Tri-Vananda_2026_Progress-Update.html
How to use:
1. Edit the Tasks sheet: set Status (dropdown), Priority, Owner, Due Date, Notes.
2. Rows with an empty Subtask column are main tasks; rows with a Subtask are their sub-items.
3. Mark a subtask complete by setting its Status to Done.
4. Key Dates sheet drives the countdown chips on the dashboard.
5. Add new tasks by inserting rows — keep the same Section names to group correctly.
6. Save this file, then open the dashboard and click 'Update from Excel'.