## Tasks
Section | Task | Subtask | Status | Priority | Owner | Due Date | Notes | Link | New
Task Management | Update 20251201 Tri Vananda Marketing Plan.xlsx |  | Done | High | Yaya | 2026-07-14 | updated 17/07/2026
Task Management | Update 20251201 Tri Vananda Marketing Plan.xlsx | Update due date, and calendar for H2 | In progress |  |  | 2026-07-17
Task Management | Create Master Strategic Campaign — Montara perspective |  | Done | High | Tree | 2026-07-21 | Science ¦ Art ¦ Soul framework across all brands and touchpoints
Task Management | Create Master Strategic Campaign — Montara perspective | Define Science ¦ Art ¦ Soul framework | Done |  |  | 2026-07-17
Task Management | Create Master Strategic Campaign — Montara perspective | Map framework across all brands and touchpoints | Done |  |  | 2026-07-17
Task Management | Create Master Strategic Campaign — Montara perspective | Draft campaign narrative and creative territories | Done |  |  | 2026-07-17
Task Management | Create Master Strategic Campaign — Montara perspective | Present for approval | Done |  |  | 2026-07-21
Events | Secure GWS Collaboration contract |  | Done | High | Tree | 2026-08-21 | Foundation for all GWS activity — prioritise
Events | Secure GWS Collaboration contract | Agree scope and format of collaboration | Done |  |  | 2026-07-24
Events | Secure GWS Collaboration contract | Negotiate commercial terms | Done |  |  | 2026-07-31
Events | Secure GWS Collaboration contract | Legal review | Done |  |  | 2026-08-14
Events | Secure GWS Collaboration contract | Sign contract | Done |  |  | 2026-08-21
Events | BEING 2026 |  | In progress | High | Fon | 2026-09-02 | Wednesday 2 September 2026 - booth เล็กสุดเท่าที่ทำได้
Events | BEING 2026 | Get booth and sponsorship package | Done |  |  | 2026-07-24
Events | BEING 2026 | Booth production, design and collateral preparation | Done |  |  | 2026-07-31
Events | BEING 2026 | Collateral print | Done |  |  | 2026-07-31
Events | BEING 2026 | Giveaway | Done |  |  | 2026-07-31
Events | BEING 2026 | PRU Farm Festival advertising at the booth | In progress |  |  | 2026-07-27 | maybe show video teaser
Events | BEING 2026 | CEO approval | Done |  |  | 2026-07-31
Events | BEING 2026 | Secure contract | Done |  |  | 2026-07-31
Events | BEING 2026 | Lead-capture method ready | In progress |  |  | TBC
Events | BEING 2026 | Post-event follow-up | In progress |  |  | TBC
Events | PRU Farm Festival |  | In progress | High | Fon | 2026-11-01 | Sunday 1 November 2026 — collaborate to support them
Events | PRU Farm Festival | Agree support scope with festival team | Done |  |  | 2026-07-10
Events | PRU Farm Festival | Align with the working team | Done |  |  | 2026-07-31 | Vendor co-ordination support · Activities support · Manpower support · TVND brand presence at festival
Events | PRU Farm Festival | Event preparation with budget | In progress |  |  | 2026-08-07
Events | PRU Farm Festival | Finalize Sponsor package with PRU | Not started |  |  | 2026-08-14
Events | PRU Farm Festival | CEO approval | Not started |  |  | 2026-08-11
Events | PRU Farm Festival | Secure sponsorship with PRU | Not started |  |  | 2026-08-12
Events | PRU Farm Festival | On-day operations plan | Not started |  |  | TBC
Events | GWS Tours — CLP / CH |  | In progress | High | Fon | 2026-11-09 | Monday 9 November 2026 - Yaya ดู Content
Events | GWS Tours — CLP / CH | Event preparation with budget, co-ordinate with working team | In progress |  |  | 2026-08-14 | Intro session at CLP (masterplan + Residential Villa showcase) · CLP estate tour · Buggy cruise through Tri Vananda landscape · Farm tour · Move to Trisara: PATAMA wellness tour and lunch · Guest logistics: transport, timing, pax
Events | GWS Tours — CLP / CH | Upgraded well spring content | Not started |  |  | 2026-08-14 | exhibition panel to communicate with guests/production
Events | GWS Tours — CLP / CH | budget | Not started |  |  | 2026-08-14
Events | GWS Tours — CLP / CH | CEO approval | Not started |  |  | 2026-08-19
Events | GWS Tours — CLP / CH | wellspring content production | Not started |  |  | TBC
Events | GWS Tours — CLP / CH | update project master plan & PATAMA resident rendering | Not started |  |  | TBC | p'tree
Events | GWS Tours — CLP / CH | Full run-of-show rehearsal | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS |  | In progress | High | Fon |  | Date TBC - ทำ journey ลูกค้า GWS ไม่มีทัวร์ แต่ลูกค้ามีทัวร์ ไปตรงไหนเจออะไรบ้าง เช่น GWS จะได้ไป CLP แล้ว แต่จะยังไม่ได้มาที่ฟาร์ม ลูกค้ามา 4 โมง GWS เริ่ม 5 โมง
Events | Exclusive Dinner at the Farm — GWS | Confirm date (11 Nov 2026) | Done |  |  | 2026-08-14
Events | Exclusive Dinner at the Farm — GWS | CEO approval | In progress |  |  | 2026-08-19
Events | Exclusive Dinner at the Farm — GWS | Collaborate with partners for guest list | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Invitations out | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Menu with Alberto and Chef Im | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Farm tour | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Cocktail reception | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Dinner | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | Entertainment | Not started |  |  | TBC
Events | Exclusive Dinner at the Farm — GWS | On-day operations plan | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media |  | In progress | High | Fon |  | Date TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Confirm date (tentative date: 14 Nov 2026) | In progress |  |  | 2026-08-14
Events | Exclusive Dinner — Buyers, Partners & Media | CEO approval | In progress |  |  | 2026-08-19
Events | Exclusive Dinner — Buyers, Partners & Media | Collaborate with partners for guest list | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Invitations out | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Menu with Alberto and Chef Im | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Property tour (CLP + Tri Vananda) | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Cocktail reception | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Dinner | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | Entertainment | Not started |  |  | TBC
Events | Exclusive Dinner — Buyers, Partners & Media | On-day operations plan | Not started |  |  | TBC
New Online Ad Campaign | New campaign — Wellness theme |  | In progress | High | Tree | 2026-07-31 | Science ¦ Art ¦ Soul
New Online Ad Campaign | New campaign — Wellness theme | Creative concept from Science ¦ Art ¦ Soul | In progress |  |  | 2026-07-31
New Online Ad Campaign | New campaign — Wellness theme | Landing Page | Not started |  |  | 2026-07-31
New Online Ad Campaign | New campaign — Wellness theme | Ad copy and visuals produced | Not started |  |  | 2026-07-31
New Online Ad Campaign | New campaign — Wellness theme | Launch | Not started |  |  | 2026-07-31
Marketing Collateral | PATAMA Residences CGIs |  | In progress | High | Yaya |  | ยังขาดภาพ environment โดยรอบ เช่น มโนรา ญาญ่าไป followup ข้อมูลให้คนที่ทำ rendering ต่อ แล้วก็ไปขอ approve จากคุณกิตต่อ
Marketing Collateral | PATAMA Residences CGIs | Quotation and timeline | Done |  |  | 2026-08-07 | ตามคุณโจ๊ะให้ทำ QT และเอาภาพไปให้คนทำ mockup ต่อ
Marketing Collateral | PATAMA Residences CGIs | CEO approval | In progress |  |  | 2026-08-11
Marketing Collateral | PATAMA Residences CGIs | Brief renderer: views, mood, count | In progress |  |  | 2026-08-14
Marketing Collateral | PATAMA Residences CGIs | Draft review rounds | In progress |  |  | 2026-09-18
Marketing Collateral | PATAMA Residences CGIs | Final delivery | In progress |  |  | 2026-09-25
Marketing Collateral | Tower Sign |  | In progress | High | Yaya |  | มีแบบมีราคา อยากเอาแบบอัปเดต โลโก้ให้เขา เว้นที่ไว้ที่นึงเอาจำปาออกแล้วเอา PATAMA ไปใส่ ไม่ผ่านพี่ส้มแล้ว เอาแบบไปให้คุณอดัมแล้วให้เขาไปคุยกับผู้รับเหมาออกราคาอัปเดตให้ต่อ แล้วดูว่า process ต่อไปเป็นยังไงต่อ
Marketing Collateral | Tower Sign | Signage design with logos | Done |  |  | 2026-08-06
Marketing Collateral | Tower Sign | Tri Vananda + CLP confirm logo | Done |  |  | 2026-08-13
Marketing Collateral | Tower Sign | Update quotation and timeline | In progress |  |  | 2026-08-13
Marketing Collateral | Tower Sign | Select contractor | In progress |  |  | 2026-08-18
Marketing Collateral | Tower Sign | CEO approval | In progress |  |  | 2026-08-25
Marketing Collateral | Tower Sign | Fabrication and installation oversight | In progress |  |  | TBC
Marketing Collateral | New Asset Library |  | Done | High | Yaya |  | จดในโน้ต ดูไทม์ไลน์ตาม PR Agency
Marketing Collateral | New Asset Library | Audit existing assets | Done |  |  | 2026-08-14
Marketing Collateral | New Asset Library | Define folder and naming structure | Done |  |  | 2026-08-14
Marketing Collateral | New Asset Library | Migrate and tag | Done |  |  | 2026-08-14
Marketing Collateral | Nanda A6 photos |  | Done | High | Tung
Marketing Collateral | Nanda A6 photos | Shot list and styling | Done
Marketing Collateral | Nanda A6 photos | Shoot | Done |  |  | 2026-07-24
Marketing Collateral | Nanda A6 photos | Select and retouch | Done |  |  | 2026-07-31
Marketing Collateral | Nanda A6 photos | Add to asset library | Done |  |  | TBC
Marketing Collateral | Nanda G88 photos |  | Done | High | Tung
Marketing Collateral | Nanda G88 photos | Shot list and styling | Done |  |  | 2026-08-06
Marketing Collateral | Nanda G88 photos | Shoot | Done |  |  | 2026-08-13
Marketing Collateral | Nanda G88 photos | Select and retouch | Done |  |  | 2026-08-20
Marketing Collateral | Nanda G88 photos | Add to asset library | Done |  |  | TBC
Marketing Collateral | B1-19-20 VDO |  | Done |  |  | 2026-08-09 | คุยไทม์ไลน์กับครีม
Marketing Collateral | G88 VDO |  | Done |  |  | 2026-08-08 | พี่ตั๋งไปคุยไทม์ไลน์กับครีมและพี่กิ๊ฟ
Marketing Collateral | Marketing Item Directory |  | Done | High | Yaya |  | Update: 14 July 2026 - ดูไทม์ไลน์กับช่วงที่ทำ PR, ไฟล์ต่างๆ ดิจิทัล, พี่ฝนดู physical
Marketing Collateral | Marketing Item Directory | Inventory all marketing items | Done |  |  | 2026-08-31
Marketing Collateral | Marketing Item Directory | Digital | Done |  |  | 2026-07-17
Marketing Collateral | Marketing Item Directory | Physical | Done |  | Fon
Marketing Collateral | Marketing Item Directory | Build directory: location, owner, stock | Done |  |  | 2026-08-31
Marketing Collateral | Marketing Item Directory | Set review cadence | Done |  |  | 2026-08-31
Marketing Collateral | Event Co-ordination SOP |  | Not started | High | Fon
Marketing Collateral | Event Co-ordination SOP | Map event workflow: brief → budget → vendors → on-day → wrap | Not started |  |  | 2026-08-31
Marketing Collateral | Event Co-ordination SOP | Templates and checklists | Not started |  |  | 2026-08-31
Marketing Collateral | Event Co-ordination SOP | Circulate and train | Not started |  |  | 2026-08-31
Marketing Collateral | Giveaways order — Tote bags |  | In progress | High | Fon |  | Two versions: one premium, one giveaway
Marketing Collateral | Giveaways order — Tote bags | Get quotations and create email with details | Done |  |  | 2026-07-20
Marketing Collateral | Giveaways order — Tote bags | Send to Khun Kitt for approval | Done |  |  | 2026-07-22
Marketing Collateral | Giveaways order — Tote bags | Place order: premium + giveaway versions | Done
Marketing Collateral | Giveaways order — Tote bags | QC on delivery | In progress
Content Marketing | Q3–Q4 2026 social media plans |  | In progress | High | Yaya |  | Monthly plans through year-end, aligned to Sep–Dec launch arc
Content Marketing | Q3–Q4 2026 social media plans | Monthly themes aligned to Sep–Dec launch arc | Done |  |  | 2026-08-31
Content Marketing | Q3–Q4 2026 social media plans | Content calendar per month | Done |  |  | 2026-08-31
Content Marketing | Q3–Q4 2026 social media plans | Production and scheduling | In progress |  |  | 2026-08-31
Content Marketing | Q3–Q4 2026 social media plans | Monthly review | In progress |  |  | 2026-08-31
Content Marketing | Q3 2026 Quarterly Newsletter |  | In progress | High | Yaya |  | CLP, PATAMA, GWS
Content Marketing | Q3 2026 Quarterly Newsletter | Story selection | In progress |  |  | 2026-09-30
Content Marketing | Q3 2026 Quarterly Newsletter | Copy and design | In progress |  |  | 2026-09-30
Content Marketing | Q3 2026 Quarterly Newsletter | Approval | Not started |  |  | 2026-09-30
Content Marketing | Q3 2026 Quarterly Newsletter | Send and report | Not started |  |  | 2026-11-01
PR | Secure contract with J/PR |  | In progress | High | Tree
PR | Secure contract with J/PR | Finalize scope and fees | In progress |  |  | 2026-07-24
PR | Secure contract with J/PR | Contract review | In progress |  |  | 2026-08-07
PR | Secure contract with J/PR | Sign and kickoff | In progress |  |  | 2026-08-14
PR | Q3–Q4 2026 PR strategy and plan |  | In progress | High | Tree
PR | Q3–Q4 2026 PR strategy and plan | Narrative and key messages | In progress |  |  | TBC
PR | Q3–Q4 2026 PR strategy and plan | Channel and media targets | In progress |  |  | TBC
PR | Q3–Q4 2026 PR strategy and plan | Agency brief | In progress |  |  | TBC
PR | Q3–Q4 2026 PR strategy and plan | Approve plan | In progress |  |  | TBC
PR | Press kit / media fact sheet refresh |  | In progress | High | Tree |  | Ready for J/PR the day the contract signs
PR | Press kit / media fact sheet refresh | Audit current kit | In progress
PR | Press kit / media fact sheet refresh | Update facts, bios, images | In progress
PR | Press kit / media fact sheet refresh | Package ready for J/PR day one | In progress
PATAMA | Source creative agency |  | Not started | High | Tree
PATAMA | Source creative agency | Shortlist | Not started
PATAMA | Source creative agency | Brief and proposals | Not started
PATAMA | Source creative agency | Select and contract | Not started
PATAMA | YPO Retreat Package |  | In progress | High | Tree
PATAMA | YPO Retreat Package | Define programme and inclusions | Not started
PATAMA | YPO Retreat Package | Pricing | Not started
PATAMA | YPO Retreat Package | Sales one-pager | Not started
PATAMA | GWS Retreat Package |  | In progress | High | Tree
PATAMA | GWS Retreat Package | Define programme and inclusions (tailored to GWS delegates) | Not started
PATAMA | GWS Retreat Package | Pricing | Not started
PATAMA | GWS Retreat Package | Sales one-pager | Not started
PATAMA | Marketing collateral |  | Not started | High | Tree
PATAMA | Marketing collateral | Website | Not started
PATAMA | Marketing collateral | PATAMA Brochure — CLP Retreat | Not started
PATAMA | Marketing collateral | PATAMA Brochure — Trisara Retreat | Not started
PATAMA | Marketing collateral | PATAMA Wellness at Trisara menu | Not started
PATAMA | Social media |  | Not started | High | Tree
PATAMA | Social media | Channel setup / handle strategy | Not started
PATAMA | Social media | Launch content set | Not started
PATAMA | Social media | Ongoing calendar | Not started
PATAMA | Digital ad campaign |  | Not started | High | Tree
PATAMA | Digital ad campaign | Audience and budget | Not started
PATAMA | Digital ad campaign | Creative | Not started
PATAMA | Digital ad campaign | Launch and optimize | Not started
PATAMA | Products for sale and giveaway |  | Not started | High | Tree |  | From local suppliers — e.g. wan sao long
PATAMA | Products for sale and giveaway | Source local suppliers (wan sao long etc.) | Not started
PATAMA | Products for sale and giveaway | Select and price | Not started
PATAMA | Products for sale and giveaway | Order and packaging | Not started

## Key Dates
Label | Date
Marketing Plan xlsx due | 2026-07-14
BEING 2026 | 2026-09-02
PRU Farm Festival | 2026-11-01
GWS Tour — Farm | 2026-11-09
GWS Tour — Local Roots | 2026-11-14

## ReadMe
TRI VANANDA — TASK LIST DATA FILE
This file feeds the dashboard: Tri-Vananda_2026_Progress-Update.html
How to use:
1. Edit the Tasks sheet: set Status (dropdown), Priority, Owner, Due Date, Notes.
2. Rows with an empty Subtask column are main tasks; rows with a Subtask are their sub-items.
3. Mark a subtask complete by setting its Status to Done.
4. Key Dates sheet drives the countdown chips on the dashboard.
5. Add new tasks by inserting rows — keep the same Section names to group correctly.
6. Save this file, then open the dashboard and click 'Update from Excel'.